## Introduction
Generic Hazard Log
NOTES:
Hazard Log contents
Hazard identifier | HAZ_01
Hazard title | Denial of service targeted at the communication service.
Hazard description | A denial of service attack floods the communication channels with information, the drone will try at least to verify the information to check if it's valid or not and will not be able to process all information.
Hazard consequence | This flooding of the communication lines can lead to the drone not updating calibration parameters, as the valid communications may be lost due to physical hardware restrictions (RAM). Long term, this can lead to drone instability.
Hazard cause(s) | An internal or external botnet responsible for the denial of service.
Origin | Network monitoring
Existing safety measures | Blacklist of known malicious ip's.
Broadly acceptable | No
Likelihood of happening | Possible
Consequence | Major
Risk ranking | Risk level for DoS: Undesirable, 7 / 10
State | Open

## Cover
Hazard Log
IDENTIFICATION
PROJECT NAME: |  | Certification of Critical Systems
PROJECT CODE: |  | CECRIS
VCS REPOSITORY:
REFERENCE:
ROLE: | NAME: |  | SIGNATURE: |  | DATE:
Prepared by | Francisco Moreira |  |  |  | 2016-01-05
Verified by
Approved by
Purpose
The hazard log is used for hazard management throughout the project lifecycle. The hazard log is an ongoing tool used to manage hazards by: a) logging all identified hazards; b) recording the identification and development of appropriate controls; c) documenting defined safety requirements; d) providing traceability to supporting evidence; e) recording changes to hazard records or controls along with any justification for the change.
VERSION | DATE | DESCRIPTION |  | AUTHOR
- | 2016-01-05 | First version |  | Francisco Moreira
-
©2015 Copyright CRITICAL Software S.A. All Rights Reserved.
No commercial use of this template is permitted without previous request sent to cecris@criticalsoftware.com.
This work has been partially supported by the European Project FP7-2012-324334-CECRIS (CErtification of CRItical Systems) Grant Agreement no.: 324334 IAPP Marie Curie Action, 7th Framework Program http://www.cecris-project.eu

## Hazard Log
|  |  | Project: | Certification of Critical Systems | [19 empty] | Last edited on: | <date>
[24 empty] | Last edited by: | <person name>
Hazard Log
[7 empty] | Risk rank | [7 empty] | Additional safety measure |  |  |  | Risk rank after the additional safety requirements |  |  | Actions
Hazard identifier | Hazard title | Hazard descripton | Hazard consequence | Hazard cause(s) | Origin | Existing safety measures | Broadly acceptable | Justification if broadly acceptable | Likelihood of happening | Severity level | Risk ranking | State | Risk evaluation principle(s) | Risk evaluation documents | SR ID | SR Title | Demonstration state | Assumptions | Final likelihood of happening | Final severity level | Final risk ranking | Action | Responsible | Target date | Status | Notes
HZ-01 | First hazard | [7 empty] | Frequent or almost certain | Minor | Undesirable | Transferred |  |  | 1 | asd | Pending |  | Frequent or almost certain | Minor | Undesirable |  |  | 2016-01-01 | Pending input
HZ-02 | Second hazard | [7 empty] | Frequent or almost certain | Major | Intolerable |  |  |  | 2 | ccccc | Demonstrated
[9 empty] | Possible | Moderate | Tolerable

## SRAC
|  | Project: | Certification of Critical Systems |  | Last edited on: | <date>
[5 empty] | Last edited by: | <person name>
Safety-Related Application Conditions (SRACs)
SRAC ID | SRAC Title | SRAC Description | Actor Responsible | Demonstration method | Demonstration state | Demonstration evidence
1 | asd |  |  |  | Pending
2 | ccccc |  |  |  | Demonstrated

## Dashboard
Risk map before additional measures | [7 empty] | Risk map AFTER additional measures
Frequency / Consequence |  | Insignificant | Minor | Moderate | Major | Catastrophic |  | Frequency / Consequence |  | Insignificant | Minor | Moderate | Major | Catastrophic
|  | 1 | 2 | 3 | 4 | 5 |  |  |  | 1 | 2 | 3 | 4 | 5
Frequent or almost certain | 5 | 0 | 1 | 0 | 1 | 0 | 2 | Frequent or almost certain | 5 | 0 | 1 | 0 | 0 | 0 | 1
Likely | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Likely | 4 | 0 | 0 | 0 | 0 | 0 | 0
Possible | 3 | 0 | 0 | 1 | 0 | 0 | 1 | Possible | 3 | 0 | 0 | 0 | 0 | 0 | 0
Unlikely | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Unlikely | 2 | 0 | 0 | 0 | 0 | 0 | 0
Rare | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Rare | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 1 | 1 | 1 | 0 | 3 |  |  | 0 | 1 | 0 | 0 | 0 | 1
Total number of hazards: | 2

## Configuration
Hazard state
Open | The initial status assigned immediately after a hazard has been identified.
Controlled | he risk evaluation process has been completed and safety requirements have been established which are sufficient to control risk to an acceptable level. | Broadly | Likelihood | Consequence | Risk ranking matrix
Closed | The potential hazards have been determined not to be an actual hazard or to be wholly contained within another hazard so no further action is necessary. | Yes | Frequent or almost certain | Insignificant | Frequency / Consequence |  | Insignificant | Minor | Moderate | Major | Catastrophic
Transferred | The hazard has been transferred to another actor who now takes the lead in delivering the associated safety requirements for controlling the risk of the hazard. The proposer retains responsibility for managing the hazard. | No | Likely | Minor |  |  | 1 | 2 | 3 | 4 | 5
Cancelled | Compliance with all safety requirements related to the hazard has been demonstrated and any other actions associated with the hazard have been satisfactorily completed and so no further action is required. |  | Possible | Moderate | Frequent or almost certain | 5 | Tolerable | Undesirable | Intolerable | Intolerable | Intolerable
|  |  | Unlikely | Major | Likely | 4 | Tolerable | Tolerable | Undesirable | Intolerable | Intolerable
|  |  | Rare | Catastrophic | Possible | 3 | Negligible | Tolerable | Tolerable | Undesirable | Intolerable
[5 empty] | Unlikely | 2 | Negligible | Negligible | Tolerable | Tolerable | Undesirable
[5 empty] | Rare | 1 | Negligible | Negligible | Negligible | Tolerable | Tolerable
|  | Action States | SRAC States
|  | Open | Pending
|  | Closed | Demonstrated
Pending input